2025-2030 Climate Action Plan

As a thriving Trust serving 28 schools and nearly 5,000 pupils, the Diocese of Salisbury Academy Trust (DSAT) recognises our responsibility to be good stewards of God's creation and prepare our pupils for a changing world. This Climate Action Plan represents our commitment to embedding sustainability throughout our Trust's operations and educational approach, aligned with both the Department for Education's mandate that all education settings have a climate action plan by 2025 and the Church of England's commitment to achieve net zero carbon emissions in the next few years.

Our Trust values of LOVE, HOPE, and JOY guide this plan as we strive to go "beyond expectations for all of God's children" in caring for our common home. We recognise that addressing climate change is not only a practical necessity but also a moral and spiritual imperative that reflects our Christian ethos and commitment to intergenerational justice.

This plan provides a clear framework for action across four key areas: decarbonisation, adaptation and resilience, biodiversity improvement, and climate education. By implementing this plan, we aim to reduce our environmental impact, enhance our educational offerings, and contribute positively to the communities we serve.

THIS IS A SHARED AND COLLABORATIVE TRUSTWIDE PLAN THAT WILL BE PUBLISHED BY ALL OUR SCHOOLS IN DECEMBER 2025.  SCHOOLS WILL DEVELOP APPENDIX A, WHICH IS A NUANCED VERSION OF THE PLAN WITH THEIR KEY SCHOOL PRIORITIES, DURING SPRING 2026.

Key Targets:

- Net Zero Carbon 2030 target

- All schools to achieve Green Flag eco-school status by 2027

- Integration of climate and sustainability into curriculum across all schools

- Appointment of sustainability leads and green teams in every school

- Implementation of detailed energy efficiency and renewable energy programmes

- Development of climate-resilient school infrastructure

- Enhancement of biodiversity across all school grounds

- Training and development for staff in climate education

- Engagement of the wider community in our sustainability journey

1. INTRODUCTION

1.1 Context and Purpose

This Climate Action Plan has been developed in response to:

- The Department for Education's Sustainability and Climate Change Strategy, which requires all educational settings to have a sustainability lead and climate action plan by 2025

- The Church of England's commitment to achieve net zero carbon emissions by 2030

- Our responsibility as a Christian educational institution to care for God's creation

- The need to prepare our pupils for the challenges and opportunities of a changing world

- Alignment with DSAT's Estates and Sustainability Strategy which aims "to provide safe, secure and sustainable buildings that promote excellent learning spaces and behaviours that demonstrate care for the environment"

The plan provides a structured framework for reducing our environmental impact, enhancing our educational provision, and contributing positively to our communities through sustainability initiatives.

1.2 Scope

This plan applies to all 28 schools within the Diocese of Salisbury Academy Trust, serving approximately 5,000 pupils across Wiltshire and Dorset. It can be adapted and personalised by each school using the action plan at Appendix A and encompasses:

- All Trust-owned and operated buildings and facilities

- Transport used for Trust activities

- Educational programmes and curriculum development

- Staff and pupil engagement

- Community partnerships

- Procurement and supply chain considerations

1.3 Vision and Values

Our sustainability vision is informed by our Trust's core values:

LOVE: Embracing our responsibility to care for creation and future generations

HOPE: Taking positive action to create a better, more sustainable future

JOY: Finding fulfilment in living and learning sustainably

Through this plan, we aim to become a leader in sustainable education, demonstrating that environmental responsibility and educational excellence can go hand in hand.

1.4 Strategic Objectives

- Reduce our carbon emissions and environmental impact

- Build resilience to climate change impacts

- Enhance biodiversity across our school estates

- Deliver excellent climate education and develop eco-literacy

- Engage our whole community in sustainability initiatives

- Connect our environmental actions with our Christian ethos and values

2. GOVERNANCE AND LEADERSHIP

To ensure success in the implementation of this plan, we have determined the following governance and leadership structure;

Sustainability Forum (reporting into Stewardship Committee)

This is composed of; Head of Estates and Operations (HoEO) Headteacher x2, Teacher x2, Hub Business Manager (HBM), Eco-School Champion, (SLT attending where appropriate).  Responsibilities will include strategic oversight, policy development, resource allocation, monitoring and reporting.  This group will meet three times per year with an annual strategic review.

Trust Sustainability Lead

Our Trust-level Sustainability Lead coordinates implementation across all schools.  This includes planning, school support including CPL, reporting and developing external partnerships.  The Trust Sustainability Lead will support all schools in achieving Green Flag status by 2027.

School-Level Sustainability Leads

Each school has appointed a Sustainability Lead.  Their responsibilities are the development and implementation of the school-level action plan (Appendix A), coordination of the Eco-School Team, school level CPL and ensuring integration with other improvement plans.

Eco-School Teams

Eco-School Teams or Green Teams are established in each school.  This includes staff and pupil representation from all year groups.  The teams meet regularly (at least 6 times per year) and work together to enact the school level plan. Our Eco-school Teams work in collaboration with other pupil leadership groups within their own schools and across other schools at Hub and Trust level.

Accountability Framework

Schools are expected to produce an annual sustainability report to the Trust Sustainability Lead which outlines progress on their school action plan and towards Green Flag status.

The Trust Sustainability Lead will provide progress updates to Trust Sustainability Committee, and this will form an annual report to the Trust Board.

Schools are also expected to provide regular updates to their wider communities through websites, social media, newsletters and other communications.

3. FUNDING AND RESOURCES

Trust Level

The Trust has ensured that the commitment to sustainability is budgeted for to ensure this plan can be enacted.  This integrates with existing capital and operational budgets including School Condition Allocation (SCA) funding.

School Level

Schools are provided with guidance as how to allocate their funding – General Annual Grant (GAG) and Devolved Formula Capital (DFC) as well as revenue funding.  Allocation for sustainability should align with the sustainability action plan and other academy improvement plans.

Wherever possible, schools are encouraged to share resources across schools and to support pupils in leading their own fundraising initiatives.

External Funding

The Trust is working to secure external funding through engagement in the Public Sector Decarbonisation Scheme, proactively seeking grant opportunities, supporting school led applications and building partnerships with charitable and corporate organisations both locally and nationally.

Resource Sharing

We have established a Trust-wide resource bank which is accessible to all schools.  Across Hubs and the wider Trust, we actively share equipment and expertise.  We are working towards collaborative purchasing and the implementation of a Trust Marketplace to recycle furniture and other resources.

4. ASSOCIATED POLICIES AND PLANS

This plan aligns and should be read in conjunction with the following Trust policies and plans.

- DSAT Estates and Sustainability Strategy: Outlines the Trust's approach to maintaining safe, secure, and sustainable buildings.

- DSAT Asset Management Plan: Framework for managing the Trust's physical assets.

- DSAT Procurement Policy: Guidelines for sustainable and ethical purchasing.

IMPLEMENTATION PLAN

Diocese of Salisbury Academy Trust Climate Action Plan 2025-2030

This implementation plan outlines specific actions, responsibilities, timelines, and resources required to deliver the DSAT Climate Action Plan. Actions are organised according to the plan's main sections and prioritised over the 2025-2030 period.

- GOVERNANCE AND LEADERSHIP ACTIONS

| Action | Responsibility | Timeline | Resources Required | Success Criteria |
| --- | --- | --- | --- | --- |
| 1.1 Establish Trust Sustainability Committee with clear terms of reference | CEO/CFOO | Jan-26 | Board time, governance framework | Committee established with representation from Board, leadership team, and operational staff |
| 1.2 Appoint Trust Sustainability Lead | CEO/CFOO | Jan-26 | Staffing budget, job description | Suitably qualified individual appointed with clear remit |
| 1.3 Develop Trust-wide Sustainability Policy | Trust Sustainability Lead | Mar-26 | Policy development time | Policy approved by Board and communicated to all schools |
| 1.4 Appoint School Sustainability Leads in all schools | Headteachers | Jan-26 | Staff time allocation, role descriptions | All schools have a named Sustainability Lead |
| 1.5 Establish Green Teams in all schools | School Sustainability Leads | Mar-26 | Meeting time, recruitment materials | Active Green Teams with staff and pupil representation |
| 1.6 Develop sustainability reporting framework | Trust Sustainability Lead | Mar-26 | Data collection systems | Clear, consistent reporting mechanism in place |
| 1.7 Provide initial training for all Sustainability Leads | Trust Sustainability Lead | Mar-26 | Training budget, training materials | 100% of Sustainability Leads trained |
| 1.8 Integrate sustainability targets into school improvement plans | CFOO/Headteachers | Apr-26 | Planning time | All school improvement plans include sustainability targets |

- DECARBONISATION ACTIONS

| Action | Responsibility | Timeline | Resources Required | Success Criteria |
| --- | --- | --- | --- | --- |
| 2.1 Conduct energy audits across all schools | CFOO/LHBM | Jul-26 | Audit budget, external expertise | Comprehensive energy data available for all sites |
| 2.2 Install smart meters in all schools | LHBM/HBMs | Dec-26 | Installation budget | 100% of schools with smart meters |
| 2.3 Develop decarbonisation roadmap through Energy Audits and Renewables Assessments | LHBM/External consultant | Dec-26 | Consultancy budget | Detailed roadmap with costed measures for each site |
| 2.4 Switch to 100% renewable electricity tariffs | CFOO/Procurement | Dec-25 | Procurement budget | All electricity contracts on renewable tariffs |
| 2.5 Implement first phase of LED lighting upgrades | LHBM/HBMs | Jul-25 | Capital budget, SCA funding | 50% of schools upgraded to LED lighting |
| 2.6 Develop school travel plans | School Sustainability Leads | Sep-26 | Staff time, planning templates | All schools with active travel plans |
| 2.7 Implement DSAT Marketplace for furniture recycling | HBMs/Premises Manager | Sep-25 | Digital platform, storage solutions | Platform operational with regular exchanges |
| 2.8 Conduct feasibility study for solar PV installations | CFOO/External consultant | Jan-27 | Consultancy budget | Feasibility assessments completed for all suitable sites |
| 2.9 Apply for external funding for renewable energy projects | Trust Sustainability Lead | Ongoing from Mar-26 | Bid writing capacity | At least 5 successful funding applications by 2028 |
| 2.10 Implement first phase of solar PV installations | CFOO/LHBM | 2027-2028 | Capital budget, grant funding | Solar PV installed on 30% of suitable schools |
| 2.11 Develop and implement sustainable procurement policy | CFOO/Procurement | Apr-26 | Staff time, policy development | Policy in place and applied to all major contracts |
| 2.12 Implement waste reduction and recycling programme | LHBM/HBMs | Sep-26 | Bin infrastructure, signage | 50% reduction in waste to landfill by 2028 |

- ADAPTATION AND RESILIENCE ACTIONS

| Action | Responsibility | Timeline | Resources Required | Success Criteria |
| --- | --- | --- | --- | --- |
| 3.1 Conduct climate vulnerability assessments for all schools | LHBM/External consultant | October 2025 | Assessment budget | All schools with completed assessments |
| 3.2 Develop climate-informed business continuity plans | HoEO/HBMs | March 2026 | Planning time | All schools with updated continuity plans |
| 3.3 Assess overheating risk in all buildings | LHBM/External consultant | May 2026 | Assessment budget | Thermal comfort assessment complete for all schools |
| 3.4 Implement passive cooling measures in priority buildings | LHBM/HBMs | 2026-2027 | Capital budget | High-risk buildings addressed |
| 3.5 Conduct flood risk assessments for vulnerable sites | LHBM/External consultant | June 2026 | Assessment budget | All vulnerable sites assessed |
| 3.6 Implement water efficiency measures | LHBM/HBMs | 2026-2027 | Maintenance budget | 20% reduction in water consumption |
| 3.7 Develop extreme weather protocols | CFOO/H&S Lead | September 2026 | Staff time | Protocols in place and staff trained |
| 3.8 Implement sustainable drainage features in priority sites | LHBM/External contractor | 2027-2028 | Capital budget | SuDS installed at high-risk sites |
| 3.9 Conduct air quality monitoring in urban schools | Trust Sustainability Lead | Jan-27 | Monitoring equipment | Data available for all urban schools |
| 3.10 Integrate climate adaptation into Asset Management Plan | HoEO/LHBM | Apr-27 | Staff time | Adaptation measures included in all capital planning |

- BIODIVERSITY AND ENVIRONMENTAL ENHANCEMENT ACTIONS

| Action | Responsibility | Timeline | Resources Required | Success Criteria |
| --- | --- | --- | --- | --- |
| 4.1 Conduct biodiversity surveys of all school grounds | School Sustainability Leads/External expert | 2025-2026 | Survey budget | Baseline biodiversity data for all schools |
| 4.2 Develop school-specific biodiversity action plans | School Sustainability Leads | Sep-27 | Planning time, templates | All schools with action plans |
| 4.3 Implement first phase of tree planting (1,000 trees) | HBMs/Green Teams | 2026-2027 | Tree budget, planting equipment | 1,000 trees planted and established |
| 4.4 Establish wildflower areas in all schools | School Sustainability Leads | Spring-27 | Seed budget, ground preparation | Wildflower areas in 80% of schools |
| 4.5 Install wildlife features (bird boxes, bug hotels) | Green Teams | 2026-2027 | Materials budget | Wildlife features in all schools |
| 4.6 Eliminate pesticide use across all sites | HBMs/Premises staff | Dec-26 | Training, alternative methods | Zero pesticide use |
| 4.7 Establish food growing areas in all primary schools | School Sustainability Leads | 2026-2027 | Garden infrastructure, soil | Functional growing areas in all primary schools |
| 4.8 Implement rainwater harvesting in pilot schools | LHBM/HBMs | 2027-2028 | Installation budget | Systems in 30% of schools |
| 4.9 Train staff in Forest School approaches | CPD Lead | 2026-2028 | Training budget | At least one trained staff member per school |
| 4.10 Create outdoor learning spaces in all schools | HBMs/School Sustainability Leads | 2026-2028 | Capital budget | Dedicated spaces in all schools |
| 4.11 Establish Trust-wide tree planting programme (5,000 trees by 2030) | Trust Sustainability Lead | 2026-2030 | Tree budget, volunteer time | 5,000 trees planted |

- CLIMATE EDUCATION ACTIONS

| Action | Responsibility | Timeline | Resources Required | Success Criteria |
| --- | --- | --- | --- | --- |
| 5.1 Review current curriculum for sustainability content | Curriculum Lead | Sep-26 | Staff time | Mapping complete for all year groups |
| 5.2 Develop cross-curricular sustainability resources | Trust Sustainability Lead/Curriculum Lead | Jan-27 | Resource development time, materials | Resource bank available to all schools |
| 5.3 Register all schools with Eco-Schools programme | School Sustainability Leads | Mar-26 | Registration fees | 100% of schools registered |
| 5.4 Provide carbon literacy training for all staff | Trust Sustainability Lead | 2026-2027 | Training budget, release time | 80% of staff trained |
| 5.5 Integrate climate education into school policies | Headteachers | Apr-26 | Policy review time | All relevant policies updated |
| 5.6 Establish environmental topic weeks | Curriculum Lead | 2026-2027 | Planning time, resources | Annual events in all schools |
| 5.7 Create pupil environmental leadership programme | Trust Sustainability Lead | Sep-26 | Programme development, resources | Programme active in all schools |
| 5.8 Develop partnerships with environmental organisations | Trust Sustainability Lead | 2025-2026 | Partnership management time | At least 5 active partnerships |
| 5.9 Provide subject-specific CPD for teachers | CPD Lead | 2026-2027 | Training budget | Subject-specific training delivered |
| 5.10 Support schools to achieve Green Flag status | Trust Sustainability Lead | 2027 | Support time, resources | All schools with Green Flag by 2027 |
| 5.11 Organise annual environment conference | Trust Sustainability Lead | July each year from 2026 | Event budget, venue | Well-attended annual conference |

- COMMUNITY ENGAGEMENT ACTIONS

| Action | Responsibility | Timeline | Resources Required | Success Criteria |
| --- | --- | --- | --- | --- |
| 6.1 Develop sustainability communications strategy | Trust Sustainability Lead | Oct-26 | Strategy development time | Strategy approved and implemented |
| 6.2 Create dedicated sustainability section on Trust website | Trust Sustainability Lead | Dec-26 | Web development resources | Section live and regularly updated |
| 6.3 Develop community partnerships for environmental projects | Trust Sustainability Lead | 2026-2027 | Partnership development time | At least one partnership per school |
| 6.4 Organise community environmental action days | School Sustainability Leads | From Spring 2026 | Event resources, publicity | At least one event per school per year |
| 6.6 Establish links with parish environmental initiatives | Trust Sustainability Lead | 2025-2026 | Coordination time | Active links with relevant parishes |
| 6.7 Join regional and national sustainability networks | Trust Sustainability Lead | 2025-2026 | Membership fees, attendance time | Active participation in key networks |
| 6.8 Develop pupil-led community awareness campaigns | School Sustainability Leads | From Sep-26 | Campaign resources | At least one campaign per school per year |
| 6.10 Create sustainability newsletter | Trust Sustainability Lead | Quarterly from Jan-26 | Production time, distribution resources | Regular newsletter with high engagement |

- MONITORING AND REPORTING ACTIONS

| Action | Responsibility | Timeline | Resources Required | Success Criteria |
| --- | --- | --- | --- | --- |
| 7.1 Establish carbon emissions baseline | Trust Sustainability Lead | Jul-26 | Data collection resources | Robust baseline for all schools |
| 7.2 Develop monitoring framework and KPIs | Trust Sustainability Lead | Sep-26 | Framework development time | Framework approved and implemented |
| 7.3 Implement energy management software | CFOO/LHBM | Dec-26 | Software budget, training | System operational in all schools |
| 7.4 Conduct annual carbon footprinting | Trust Sustainability Lead | Annually from Jul-26 | Data collection resources | Annual data available for all schools |
| 7.5 Produce annual sustainability report | Trust Sustainability Lead | Annually from Sep-26 | Report production time | Comprehensive report published |
| 7.6 Review and update Climate Action Plan | Trust Sustainability Committee | Annually from May-26 | Review time | Plan updated to reflect progress |
| 7.7 Conduct external verification of carbon reporting | CFOO | Biennially from 2027 | Verification budget | Independent verification complete |
| 7.8 Report progress to Board of Trustees | Trust Sustainability Lead | Quarterly | Reporting time | Regular reporting established |
| 7.9 Collect and share case studies of good practice | Communications Lead | Ongoing from Jan-26 | Case study development time | Library of case studies available |
| 7.10 Conduct mid-term evaluation of Climate Action Plan | External consultant | Jan-28 | Evaluation budget | Comprehensive evaluation report |

- FUNDING AND RESOURCES ACTIONS

| Action | Responsibility | Timeline | Resources Required | Success Criteria |
| --- | --- | --- | --- | --- |
| 8.1 Develop "prioritisation matrix" for sustainability projects | CFOO/LHBM | May-26 | Development time | Matrix approved and in use |
| 8.2 Create database of potential funding sources | Trust Sustainability Lead | Sep-26 | Research time | Comprehensive database available |
| 8.3 Apply for Public Sector Decarbonisation Scheme funding | CFOO/Trust Sustainability Lead | Annually from 2026 | Bid writing capacity | At least one successful application |
| 8.4 Investigate community energy financing options | CFOO/Trust Sustainability Lead | 2026 | Investigation time | Feasibility report produced |
| 8.5 Develop corporate sponsorship programme | CFOO | Apr-27 | Programme development time | Programme launched and sponsors secured |
| 8.6 Allocate DFC funding for sustainability projects | CFOO/Headteachers | Annually from Apr-26 | Allocation framework | Schools using DFC for sustainability |
| 8.7 Establish energy savings reinvestment mechanism | CFOO | Sep-27 | Financial mechanism development | System operational |
| 8.8 Develop partnerships with funding organisations | Trust Sustainability Lead | 2025-2027 | Partnership development time | At least 3 active funding partnerships |
| 8.9 Build capacity for grant application writing | Trust Sustainability Lead | 2025-2026 | Training, templates | Increased success rate for applications |

APPENDICES

Appendix A:  School-Specific Action Plan Template

[SCHOOL NAME] CLIMATE ACTION PLAN										Academic Year: [YYYY-YYYY]

Name of Sustainability Lead:

Current Status:

| Current Eco-Schools Award Level |  |
| --- | --- |
| Energy Performance Certificate Rating |  |
| Annual Carbon Footprint |  |
| Key Environmental Features |  |
| Existing Environmental Initiatives |  |

Action Plan

| Decarbonisation Target: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Action | Responsibility | Timeline | Resources | Success Criteria | Progress Review |

| Adaptation and Resilience Target: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Action | Responsibility | Timeline | Resources | Success Criteria | Progress Review |

| Biodiversity Target: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Action | Responsibility | Timeline | Resources | Success Criteria | Progress Review |

| Climate Education Target: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Action | Responsibility | Timeline | Resources | Success Criteria | Progress Review |

| Community Engagement Target: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Action | Responsibility | Timeline | Resources | Success Criteria | Progress Review |

CPL and support needs

Appendix B: Glossary of Terms

Carbon Footprint: The total greenhouse gas emissions caused by an individual, organisation, event, or product, expressed as carbon dioxide equivalent (CO2e).

Carbon Neutral: Achieving a balance between carbon emissions and carbon removal or offset.

Climate Adaptation: The process of adjusting to actual or expected climate and its effects.

Climate Mitigation: Actions to reduce or prevent the emission of greenhouse gases.

Climate Resilience: The ability to anticipate, prepare for, and respond to hazardous events, trends, or disturbances related to climate.

Decarbonisation: The process of reducing carbon dioxide emissions.

Eco-Schools Programme: A global programme engaging children in environmental education and action in their school and community.

Energy Audit: A detailed assessment of energy use and efficiency in a building or organisation.

Green Flag: The highest award in the Eco-Schools programme, recognising excellence in environmental action and learning.

Net Zero Carbon: Achieving a balance between the carbon emitted and the carbon removed from the atmosphere, with any remaining emissions being offset.

Renewable Energy: Energy from sources that are naturally replenishing but flow-limited, such as sunlight, wind, water, and geothermal heat.

SECR (Streamlined Energy and Carbon Reporting): A UK Government regulation that requires certain companies to report on their energy use, greenhouse gas emissions, and related information.

Sustainability: Meeting the needs of the present without compromising the ability of future generations to meet their own needs.

SuDS (Sustainable Drainage Systems): Designed to manage water quantity and quality, as well as provide amenity and biodiversity benefits.

Appendix C: Relevant Legislation and Policies

National Legislation and Policies:

- Climate Change Act 2008 (2050 Target Amendment) Order 2019: Sets the UK target of net zero greenhouse gas emissions by 2050.

- Environment Act 2021: Sets legally binding targets for biodiversity, air quality, water, and waste.

- DfE Sustainability and Climate Change Strategy (2022): Requires all education settings to have a sustainability lead and climate action plan by 2025.

- Building Regulations Part L (Conservation of Fuel and Power): Sets minimum energy performance requirements for new buildings and renovations.

- Public Sector Decarbonisation Scheme: Government funding for public sector organisations to reduce carbon emissions.

Church of England Policies:

- General Synod 2020 Net Zero Carbon Target: Commits the Church of England to achieve net zero carbon by 2030.

- Church of England Routemap to Net Zero Carbon by 2030: Provides guidance for churches, schools, and other Church institutions.

- Diocesan Environmental Policy: The Diocese of Salisbury's environmental commitments and actions.

Appendix D: Useful Resources and Organisations

Government and Statutory Bodies:

- Department for Education Sustainability Support for Education
https://www.gov.uk/guidance/sustainability-leadership-and-climate-action-plans-in-education  Resources, services, and tools to help develop or enhance climate action plans.

- Climate Change Committee
https://www.theccc.org.uk/  Independent advice to the UK Government on tackling climate change.

- Environment Agency
https://www.gov.uk/government/organisations/environment-agency  Environmental protection and regulation in England.

Church of England Resources:

- Church of England Environment Programme
https://www.churchofengland.org/about/environment-and-climate-change  Resources, case studies, and guidance for churches and schools.

- Diocese of Salisbury Environmental Initiatives
https://www.salisbury.anglican.org/parish-support/giving-and-fundraising/environmental-sustainability-projects

Education-Specific Organisations:

- Eco-Schools
https://www.eco-schools.org.uk/  Environmental education programme for schools.

- Let's Go Zero
https://letsgozero.org/  Campaign supporting schools to be zero carbon by 2030.

- SEEDS (Sustainability and Environmental Education in Schools)
https://se-ed.co.uk/  Support for schools to embed sustainability in education.

- Transform Our World
https://www.transform-our-world.org/  Free, curriculum-linked resources for teachers.

Technical Support and Funding:

- Salix Finance
https://www.salixfinance.co.uk/  Interest-free loans for energy efficiency measures in the public sector.

- Carbon Trust
https://www.carbontrust.com/  Support for organisations to reduce carbon emissions.

- Energy Saving Trust
https://energysavingtrust.org.uk/  Advice on energy efficiency and renewable energy.

Community and Biodiversity Organisations:

- The Wildlife Trusts
https://www.wildlifetrusts.org/  Local wildlife conservation and engagement.

- Royal Society for the Protection of Birds (RSPB)
https://www.rspb.org.uk/  Bird conservation and educational resources.

- Learning through Landscapes
https://www.ltl.org.uk/  Support for outdoor learning and school grounds development.